## Start here
Workplace inspection findings tracker
Free template from Skefto. The ratings, response times and measures here are suggested practice, not legal requirements. Check your regulator's current guidance and your own procedures.
Three linked records: Inspections, Findings, and Actions (recommendations and corrective actions). This structure is Skefto's suggested practice, not a legal requirement.
As at date |  | Type a date to see the Summary as it stood on that day. Completions, verifications and findings dated after it are ignored. Leave the formula to use today's date.
Site filter (optional) |  | Leave blank to include every site. Or type a site name exactly as it appears in the Inspections sheet.
How to use this workbook
Step 1 | Log each inspection on the Inspections sheet, including any areas or items you could not inspect and why. If an inspection was missed, enter the ID of the one that replaces it in the last input column.
Step 2 | Add one row on the Findings sheet for each finding. Record facts and a photo reference, not conclusions, and what was made safe at the time (the immediate action).
Step 3 | Add one row on the Actions sheet for each recommendation or corrective action, linked to its finding by ID. One finding can have several actions. Give each action one accountable owner (a named person or a formally designated position) and a due date. Avoid a team.
Step 4 | When an action is done, add the completion date and evidence on the Actions sheet. Then ask someone other than the owner to check it and record who and when.
Step 5 | If a finding repeats an earlier one, enter the earlier finding ID so the pattern shows. A finding is closed only when all of its actions are closed and verified.
Step 6 | Read the Summary sheet monthly. It uses the five measures described in the Skefto guide: coverage, open findings by rating, open and overdue corrective actions, repeat findings and verified closures.
Colour key
Yellow or white cells | Type here.
Grey cells | Formulas. Do not type over them.
Rating levels | Rename the levels to match your organisation's risk matrix. The Findings sheet and Summary sheet follow the names in this table.
Level | What the response looks like | Response time (set by your organisation)
High | Make safe now where a serious hazard or unsafe work practice is found, then fix urgently.
Medium | Fix by a set date, with an interim control where the fix will take time.
Low | Schedule a corrective action with an accountable owner and a due date.
Example data: the Example (depot) sheet shows a hypothetical council depot inspection, with a finding that has two corrective actions, and its summary at two dates. It is not taken from a real site or a Skefto customer.
Published with the guide at skefto.com/blog/workplace-safety-inspection-report/

## Inspections
Inspection ID | Site or area | Planned date | Date completed | Inspector | Accompanied by (include any HSR) | Checklist and version | Areas or items not inspected, and why | New findings | Status | If missed: ID of the inspection that replaces it | In summary?
Note on A1: Example: I-001. Use one ID per inspection.
Note on C1: Example: 3 Nov 2026
Note on G1: Example: Depot workshop checklist v3. Checklists change, so record the version.
Note on H1: Example: Chemical store. Key holder absent. Rescheduled to 10 Nov.
Note on K1: Only for an inspection that did not happen on its planned date. Enter the ID of the replacement. The missed inspection still counts against coverage.

## Findings
Finding ID | Inspection ID | Date found | Location | Observation (facts, no blame) | Evidence (photo reference) | Likely cause (if known) | Rating | Made safe at the time (immediate action) | Earlier finding ID (if repeat) | Status | Corrective actions | Repeat? | Record check | Site | In summary?
Note on A1: Example: F-001. One finding per issue.
Note on D1: Example: Workshop, north emergency exit. Name the specific area, asset or task.
Note on E1: Example: Emergency exit partly blocked by stored pallets.
Note on H1: Pick from the list. The levels come from the Start here sheet.
Note on I1: What you did on the day to make the area safe. This is not the corrective action. Record each recommendation or corrective action on the Actions sheet.
Note on J1: Example: F-009. Links this finding to the earlier one so repeats show on the Summary.
Note on K1: Worked out from the finding's corrective actions on the Actions sheet, as at the date on the Start here sheet. Overdue if any action is overdue, Open if any action is open, and Closed and verified only when every action is closed and verified.
Note on L1: How many corrective actions are linked to this finding.

## Actions
Action ID | Finding ID | Recommendation or corrective action (what will be done) | Owner (named person or formally designated position) | Due date | Date completed | Completion evidence | Verified by (not the person assigned the action) | Verification date | Status | Days overdue | Record check | Finding rating | Site | In summary? | Finding logged on
Note on A1: Example: A-001. One ID per corrective action.
Note on B1: The ID of the finding this action belongs to. A finding can have several actions: use one row for each.
Note on C1: Example: Mark a pallet storage area away from the exit and brief the workshop team. Describe the fix to the cause, not only the symptom.
Note on D1: One named person or a formally designated position, such as Workshop supervisor. Avoid a team. If the owner is a position, check who holds it when the role changes hands.
Note on E1: A date set from the rating, with any approved extension recorded separately.
Note on G1: Example: Photo of the marked storage area (IMG_2044).
Note on H1: Someone other than the person assigned the action. Record who checked and what they saw.
Note on J1: Calculated as at the date on the Start here sheet. A completion or verification dated after that date is ignored.

## Summary
Monthly summary
As at
Five suggested measures for managers and officers. They are not a regulatory reporting set. Read them alongside incident and hazard reporting data.
Measure | Result | What it tells you
1. Inspections planned to date |  | Inspections with a planned date on or before the as-at date.
1. Of those, completed by the as-at date |  | Planned inspections with a completion date on or before the as-at date.
1. Coverage |  | Completed divided by planned to date. It cannot exceed 100%. A falling figure means the program is slipping.
1. Of those, completed late |  | Completed after the planned date.
1. Planned but not completed by the as-at date |  | Overdue or missed inspections, including those already rescheduled.
1. Other inspections completed (early or unplanned) |  | Completed on or before the as-at date but not counted in coverage.
1. Completed inspections with areas or items not inspected |  | Gaps in coverage. Each one needs a reason and a new date.
2. Open findings (any corrective action not yet completed) |  | Findings logged by the as-at date with at least one corrective action still open or overdue.
2. Open findings: first rating level |  | Open findings at the first level on the Start here sheet.
2. Open findings: second rating level |  | Open findings at the second level.
2. Open findings: third rating level |  | Open findings at the third level.
2. Open findings with no matching rating |  | Open findings with a blank or unrecognised rating. Fix these on the Findings sheet.
2. Findings with no corrective action recorded |  | Findings that nobody has been asked to fix. Add an action on the Actions sheet.
3. Open corrective actions |  | Corrective actions not completed by the as-at date, including overdue ones.
3. Overdue corrective actions |  | Actions past their due date and not completed by the as-at date.
3. Longest overdue (days) |  | How long the oldest overdue action has been overdue.
4. Repeat findings |  | Findings that repeat an earlier one. Group them by location, asset or cause.
5. Corrective actions closed and verified |  | Completed by the as-at date, with a named verifier and a verification date on or before it.
5. Corrective actions closed, not verified |  | Completed but not yet checked. These are claims, not confirmed fixes.
5. Share of closed actions verified |  | Verified closures divided by all closures.
5. Findings closed and verified |  | Findings whose corrective actions are all closed and verified.
Findings logged after the as-at date (excluded) |  | Shown so that nothing disappears without explanation.
Records to fix (see the Record check columns) |  | Findings and actions missing a rating, owner, due date, evidence or verifier, with inconsistent dates, or verified by the owner.
Reconciliation, findings |  | Open + closed + no action = findings logged by the as-at date. Should read OK.
Reconciliation, corrective actions |  | Open + closed actions = actions in the summary. Should read OK. If either reads Mismatch, a formula has been overwritten.
Rating level names come from the Start here sheet. Rename them there and this sheet updates.

## Example (depot)
Example: a council depot inspection
Hypothetical. The depot and its findings are invented to show how entries look. They are not taken from a real site or a Skefto customer. Ratings and timeframes are placeholders. The follow-up dates after 3 Nov are invented so the summary can show two reporting dates. Finding F-002 has two corrective actions.
Reporting date A | 2026-11-06 | Reporting date B | 2026-11-20 | Edit either date. Every figure below recalculates. Date A matches the sample report in the guide.
Inspection log
Inspection ID | Site or area | Planned date | Date completed | Inspector | Accompanied by | Checklist and version | Areas or items not inspected, and why | Rescheduled to | Status at date A | Status at date B
I-001 | Depot workshop and yard | 2026-11-03 | 2026-11-03 | Depot supervisor | Workshop supervisor; HSR | Depot workshop checklist v3 | Chemical store: key holder absent. Rescheduled as I-002.
I-002 | Chemical store | 2026-11-10 | 2026-11-11 | Depot supervisor | Store officer | Chemical store checklist v2
Findings (what was seen, and what was made safe at the time)
Finding ID | Inspection ID | Date found | Location | Observation | Rating | Made safe at the time (immediate action) | Earlier finding | Status at date A | Status at date B
F-001 | I-001 | 2026-11-03 | Vehicle bay roller door | Safety edge did not stop the door when tested. | High | Door isolated and tagged out. Vehicle moved.
F-002 | I-001 | 2026-11-03 | Workshop emergency exit | Exit partly blocked by stored pallets. Third time at this location in six months. | High | Pallets removed during the inspection. | Two earlier records
F-003 | I-001 | 2026-11-03 | Workshop | Spill kit empty. | Medium | Kit moved from the yard store.
F-004 | I-001 | 2026-11-03 | Workshop | Fire extinguisher service label two months overdue. | Medium | Gauge and seal checked. Service booked with the contractor.
Recommendations and corrective actions (what will be done for each finding, who owns it, and when)
Action ID | Finding ID | Recommendation or corrective action | Owner (named person or designated position) | Due date | Date completed | Verified by (not the person assigned the action) | Verification date | Status at date A | Status at date B
A-001 | F-001 | Replace the faulty safety edge, then re-test that the door stops and reverses on contact. | Facilities coordinator | 2026-11-10 | 2026-11-09 | Depot manager | 2026-11-10
A-002 | F-002 | Mark a pallet storage area away from the exit. | Workshop supervisor | 2026-11-13 | 2026-11-12
A-003 | F-002 | Add an exit-clear check to the workshop close-down and brief the team. | Workshop supervisor | 2026-11-17
A-004 | F-003 | Restock the workshop spill kit and add it to the monthly workshop check. | Store officer | 2026-11-17 | 2026-11-14
A-005 | F-004 | Have the contractor service the extinguisher and fit a current service label. | Facilities coordinator | 2026-11-17
Summary at the two reporting dates (calculated from the tables above)
Measure | At date A | At date B
Inspections planned to date
Of those, completed by the date
Coverage
Completed late
Completed inspections with areas not inspected
Open findings: High
Open findings: Medium
Open findings: Low
Open corrective actions
Overdue corrective actions
Repeat findings
Corrective actions closed and verified
Corrective actions closed, not verified
At date A all five corrective actions are open and none is overdue. At date B two actions are overdue, one finding is closed and verified, and one inspection was completed late.